## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Pragya Pratap | 2026-08-31 | Gemini API key was not correctly configured | Sprint 1 | Pragya Pratap | Configuration | Corrected the Gemini API key configuration | Actual date | Closed | API connection verified
2 | Pragya Pratap | 2026-09-03 | Gemini 2.5 Flash model was unavailable | Sprint 1 | Pragya Pratap | Configuration | Updated the model to Gemini 3.6 Flash | Actual date | Closed | Model response verified
3 | Pragya Pratap | 2026-09-14 | Job role not found during tool execution | Sprint 3 | Pragya Pratap | Functional | Added exception handling for invalid job roles | Actual date | Closed | Error message verified
4 | Pragya Pratap | 2026-09-17 | Tool output was not initially integrated into workflow | Sprint 4 | Pragya Pratap | Integration | Integrated Job Agent and job requirements into workflow | Actual date | Closed | Complete workflow verified
5 | Pragya Pratap | 2026-09-17 | Tool selection required request-based handling | Sprint 4 | Pragya Pratap | Functional | Implemented rule-based Tool Selector | Actual date | Closed | Tool selection verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others